## Dashboard
Task ID | Task Name | Team | Task Owner | Start Date | Due Date | Task Duration | Status | Overdue? | Comments
T001 | Prepare Q4 Financial Report | Finance | Sarah Johnson | 2026-09-02 | 2026-09-20 | 18 | Completed | FALSE | Submitted to CFO for review.
T002 | Conduct Market Research | Strategy | Sarah Johnson | 2026-09-05 | 2026-09-25 | 20 | Completed | FALSE | Draft findings ready; awaiting survey data.
T003 | Redesign Website Homepage | Strategy | David Kim | 2026-07-10 | 2026-08-05 | 26 | In Progress | TRUE | Wireframes approved; development in progress.
T004 | Update Sales Forecast for FY2026 | Finance | Sarah Johnson | 2026-09-12 | 2026-09-30 | 18 | Completed | FALSE | Final version shared with Sales Director.
T005 | Implement CRM Upgrade | Strategy | James Miller | 2026-09-15 | 2026-10-10 | 25 | In Progress | FALSE | Vendor confirmed delivery timeline.
T006 | Plan Annual Company Retreat | HR | David Kim | 2026-09-18 | 2026-10-15 | 27 | In Progress | FALSE | Venue options being shortlisted.
T007 | Review Legal for Contracts | HR | Alex Chen | 2026-08-20 | 2026-08-27 | 7 | Not Started | TRUE | Updated contracts aligned with new regulation.
T008 | Launch Social Media Campaign | Marketing | Alex Chen | 2026-09-22 | 2026-10-12 | 20 | In Progress | FALSE | Initial creatives approved, campaign scheduled.
T009 | Recruit New Data Analyst | HR | Sarah Johnson | 2026-09-23 | 2026-10-20 | 27 | Completed | FALSE | First round of interviews completed.
T010 | Conduct Employee Survey | HR | Sarah Johnson | 2026-09-24 | 2026-10-05 | 11 | In Progress | TRUE | Survey questions finalized.
T011 | Prepare Investor Presentation | Finance | David Kim | 2026-09-25 | 2026-10-02 | 7 | Completed | FALSE | Draft slides ready; awaiting financial highlights.
T012 | Upgrade Infrastructure | Strategy | Sarah Johnson | 2026-09-26 | 2026-10-30 | 34 | Completed | FALSE | External consultant engagement pending.
T013 | Evaluate Vendor Proposals for Logistics | Strategy | Emily Davis | 2026-09-27 | 2026-10-07 | 10 | In Progress | TRUE | Three proposals shortlisted for management review.
T014 | Draft Q1 Marketing Strategy | Strategy | Emily Davis | 2026-09-28 | 2026-10-18 | 20 | Completed | FALSE | Kick-off meeting scheduled next week.
T015 | Audit Internal Expense Reports | Finance | Emily Davis | 2026-09-29 | 2026-10-04 | 5 | Not Started | TRUE | Waiting for submission of all departmental reports.
T016 | Develop annual budget forecast | Finance | Sarah Johnson | 2026-08-10 | 2026-10-15 | 66 | In Progress | FALSE | Forecast assumptions under review
T017 | Reconcile quarterly accounts | Finance | David Kim | 2026-09-01 | 2026-09-25 | 24 | Completed | FALSE | Quarterly reconciliation completed
T018 | Review department expenses | Finance | James Miller | 2026-09-15 | 2026-10-06 | 21 | In Progress | TRUE | Waiting for final receipts
T019 | Prepare monthly financial report | Finance | Alex Chen | 2026-10-01 | 2026-10-20 | 19 | Not Started | FALSE | Scheduled for the next reporting cycle
T020 | Review procurement spending | Finance | Emily Davis | 2026-08-12 | 2026-09-05 | 24 | Completed | FALSE | Spending review signed off
T021 | Update cash flow projections | Finance | Sarah Johnson | 2026-10-02 | 2026-10-28 | 26 | In Progress | FALSE | Updating assumptions for Q4
T022 | Audit travel reimbursements | Finance | David Kim | 2026-08-18 | 2026-09-10 | 23 | Not Started | TRUE | Pending document collection
T023 | Build department cost model | Finance | James Miller | 2026-09-20 | 2026-10-30 | 40 | In Progress | FALSE | Model structure drafted
T024 | Validate invoice records | Finance | Alex Chen | 2026-09-05 | 2026-09-18 | 13 | Completed | FALSE | Invoice checks completed
T025 | Prepare tax documentation | Finance | Emily Davis | 2026-10-05 | 2026-11-12 | 38 | Not Started | FALSE | Documentation work not yet started
T026 | Review investment assumptions | Finance | Sarah Johnson | 2026-08-01 | 2026-09-15 | 45 | Completed | FALSE | Assumptions approved by management
T027 | Automate expense summaries | Finance | David Kim | 2026-09-22 | 2026-10-25 | 33 | In Progress | FALSE | Automation logic being tested
T028 | Review budget variances | Finance | James Miller | 2026-08-20 | 2026-09-12 | 23 | Completed | FALSE | Variance explanations documented
T029 | Create financial KPI definitions | Finance | Alex Chen | 2026-10-06 | 2026-10-24 | 18 | Not Started | FALSE | Awaiting stakeholder alignment
T030 | Consolidate regional forecasts | Finance | Emily Davis | 2026-09-10 | 2026-10-12 | 32 | In Progress | FALSE | Regional submissions being consolidated
T031 | Define strategic priorities | Strategy | Sarah Johnson | 2026-08-03 | 2026-08-28 | 25 | Completed | FALSE | Priority framework approved
T032 | Analyze competitor positioning | Strategy | David Kim | 2026-09-01 | 2026-10-10 | 39 | In Progress | FALSE | Competitor findings being reviewed
T033 | Map customer journey stages | Strategy | James Miller | 2026-08-15 | 2026-09-15 | 31 | Completed | FALSE | Journey map shared with stakeholders
T034 | Evaluate new market opportunities | Strategy | Alex Chen | 2026-10-01 | 2026-11-15 | 45 | Not Started | FALSE | Research scheduled for November
T035 | Document business processes | Strategy | Emily Davis | 2026-08-20 | 2026-09-25 | 36 | Completed | FALSE | Process documentation published
T036 | Assess digital transformation options | Strategy | Sarah Johnson | 2026-09-12 | 2026-10-18 | 36 | In Progress | FALSE | Options being compared
T037 | Review operating model | Strategy | David Kim | 2026-08-10 | 2026-09-02 | 23 | Completed | FALSE | Operating model review finalized
T038 | Prepare leadership workshop | Strategy | James Miller | 2026-10-04 | 2026-10-22 | 18 | Not Started | FALSE | Workshop agenda to be prepared
T039 | Develop strategic scorecard | Strategy | Alex Chen | 2026-09-05 | 2026-10-20 | 45 | In Progress | FALSE | Initial scorecard drafted
T040 | Assess supplier performance | Strategy | Emily Davis | 2026-08-25 | 2026-09-20 | 26 | Completed | FALSE | Supplier assessment completed
T041 | Review service delivery model | Strategy | Sarah Johnson | 2026-09-18 | 2026-10-30 | 42 | In Progress | FALSE | Delivery model options under review
T042 | Create project prioritization matrix | Strategy | David Kim | 2026-08-04 | 2026-09-01 | 28 | Completed | FALSE | Matrix reviewed by team leads
T043 | Analyze operational bottlenecks | Strategy | James Miller | 2026-10-02 | 2026-11-08 | 37 | Not Started | FALSE | Analysis planned for next sprint
T044 | Draft transformation roadmap | Strategy | Alex Chen | 2026-09-08 | 2026-10-28 | 50 | In Progress | FALSE | Roadmap milestones in progress
T045 | Coordinate employee onboarding | HR | Sarah Johnson | 2026-09-01 | 2026-09-12 | 11 | Completed | FALSE | Onboarding checklist completed
T046 | Update employee handbook | HR | David Kim | 2026-08-10 | 2026-09-05 | 26 | Completed | FALSE | Revised handbook published
T047 | Plan leadership training | HR | James Miller | 2026-09-15 | 2026-10-25 | 40 | In Progress | FALSE | Training content being prepared
T048 | Review recruitment workflow | HR | Alex Chen | 2026-10-02 | 2026-10-30 | 28 | Not Started | FALSE | Workflow review scheduled
T049 | Conduct employee engagement review | HR | Emily Davis | 2026-08-18 | 2026-09-20 | 33 | Completed | FALSE | Results shared with HR
T050 | Organize internal knowledge sessions | HR | Sarah Johnson | 2026-09-20 | 2026-10-15 | 25 | In Progress | FALSE | Session schedule being confirmed
T051 | Review compensation benchmarks | HR | David Kim | 2026-08-05 | 2026-09-10 | 36 | Completed | FALSE | Benchmark analysis finalized
T052 | Prepare workforce planning report | HR | James Miller | 2026-10-05 | 2026-11-18 | 44 | Not Started | FALSE | Planning cycle not yet started
T053 | Coordinate internship program | HR | Alex Chen | 2026-09-02 | 2026-10-05 | 33 | In Progress | TRUE | Candidate pipeline being reviewed
T054 | Refresh HR policy documentation | HR | Emily Davis | 2026-08-12 | 2026-09-22 | 41 | Completed | FALSE | Policy documents updated
T055 | Plan annual performance cycle | HR | Sarah Johnson | 2026-09-25 | 2026-11-20 | 56 | In Progress | FALSE | Cycle milestones being planned
T056 | Evaluate learning platform options | HR | David Kim | 2026-10-03 | 2026-11-05 | 33 | Not Started | FALSE | Vendor comparison not started
T057 | Launch internal mentoring program | HR | James Miller | 2026-08-20 | 2026-09-25 | 36 | Completed | FALSE | Mentoring program launched
T058 | Develop employer branding materials | HR | Alex Chen | 2026-09-08 | 2026-10-01 | 23 | In Progress | TRUE | Draft materials in review
T059 | Plan quarterly social campaign | Marketing | Sarah Johnson | 2026-09-01 | 2026-09-30 | 29 | Completed | FALSE | Campaign plan approved
T060 | Refresh website content | Marketing | David Kim | 2026-08-12 | 2026-09-10 | 29 | Completed | FALSE | Website copy updated
T061 | Develop email marketing sequence | Marketing | James Miller | 2026-09-18 | 2026-10-25 | 37 | In Progress | FALSE | Email drafts under review
T062 | Analyze campaign conversion rates | Marketing | Alex Chen | 2026-10-03 | 2026-10-28 | 25 | Not Started | FALSE | Analysis planned after campaign launch
T063 | Prepare product launch assets | Marketing | Emily Davis | 2026-08-15 | 2026-09-18 | 34 | Completed | FALSE | Launch assets delivered
T064 | Coordinate customer newsletter | Marketing | Sarah Johnson | 2026-09-22 | 2026-10-12 | 20 | In Progress | FALSE | Newsletter content being finalized
T065 | Review brand guidelines | Marketing | David Kim | 2026-08-05 | 2026-09-02 | 28 | Completed | FALSE | Guidelines approved
T066 | Plan webinar promotion | Marketing | James Miller | 2026-10-01 | 2026-10-24 | 23 | Not Started | FALSE | Promotion plan not started
T067 | Optimize landing page content | Marketing | Alex Chen | 2026-09-05 | 2026-10-05 | 30 | In Progress | TRUE | Content experiment in progress
T068 | Build marketing performance report | Marketing | Emily Davis | 2026-08-20 | 2026-09-25 | 36 | Completed | FALSE | Performance report delivered
T069 | Coordinate partner campaign | Marketing | Sarah Johnson | 2026-09-10 | 2026-10-30 | 50 | In Progress | FALSE | Partner approvals pending
T070 | Conduct audience segmentation | Marketing | David Kim | 2026-08-18 | 2026-09-20 | 33 | Completed | FALSE | Segments validated
T071 | Create case study content | Marketing | James Miller | 2026-10-04 | 2026-11-12 | 39 | Not Started | FALSE | Customer interview to be scheduled
T072 | Review social media analytics | Marketing | Alex Chen | 2026-09-12 | 2026-10-20 | 38 | In Progress | FALSE | Engagement trends being analyzed
T073 | Plan internal reporting standards | Finance | Emily Davis | 2026-09-02 | 2026-09-28 | 26 | Completed | FALSE | Reporting standards documented
T074 | Review financial control checklist | Finance | Sarah Johnson | 2026-09-10 | 2026-10-18 | 38 | In Progress | FALSE | Checklist review underway
T075 | Prepare annual audit schedule | Finance | David Kim | 2026-10-02 | 2026-11-10 | 39 | Not Started | FALSE | Schedule to be confirmed
T076 | Analyze pricing scenarios | Finance | James Miller | 2026-08-12 | 2026-09-08 | 27 | Completed | FALSE | Pricing scenarios compared
T077 | Update vendor payment tracker | Finance | Alex Chen | 2026-09-25 | 2026-10-14 | 19 | In Progress | FALSE | Payment tracker being updated
T078 | Consolidate monthly reporting inputs | Finance | Emily Davis | 2026-10-05 | 2026-10-22 | 17 | Not Started | FALSE | Waiting for monthly inputs
T079 | Review strategic initiative progress | Strategy | Sarah Johnson | 2026-09-01 | 2026-10-12 | 41 | In Progress | FALSE | Initiative owners providing updates
T080 | Assess customer feedback themes | Strategy | David Kim | 2026-08-08 | 2026-09-02 | 25 | Completed | FALSE | Feedback themes summarized
T081 | Develop process improvement backlog | Strategy | James Miller | 2026-09-20 | 2026-10-30 | 40 | In Progress | FALSE | Improvement opportunities prioritized
T082 | Review technology roadmap | Strategy | Alex Chen | 2026-10-03 | 2026-11-15 | 43 | Not Started | FALSE | Roadmap review scheduled
T083 | Document risk mitigation actions | Strategy | Emily Davis | 2026-08-15 | 2026-09-18 | 34 | Completed | FALSE | Mitigation actions documented
T084 | Prepare cross-functional project review | Strategy | Sarah Johnson | 2026-09-15 | 2026-10-26 | 41 | In Progress | FALSE | Review materials being prepared
T085 | Analyze service performance metrics | Strategy | David Kim | 2026-08-20 | 2026-09-15 | 26 | Completed | FALSE | Performance findings shared
T086 | Coordinate policy review workshop | HR | James Miller | 2026-09-10 | 2026-10-24 | 44 | In Progress | FALSE | Workshop participants being confirmed
T087 | Update new starter checklist | HR | Alex Chen | 2026-08-04 | 2026-08-28 | 24 | Completed | FALSE | Checklist refreshed
T088 | Prepare employee communications plan | HR | Emily Davis | 2026-10-01 | 2026-10-29 | 28 | Not Started | FALSE | Communications plan not yet started
T089 | Review training feedback results | HR | Sarah Johnson | 2026-09-05 | 2026-10-10 | 35 | In Progress | FALSE | Feedback analysis underway
T090 | Coordinate recruitment campaign | HR | David Kim | 2026-08-18 | 2026-09-20 | 33 | Completed | FALSE | Recruitment campaign closed
T091 | Create onboarding survey | HR | James Miller | 2026-10-04 | 2026-10-20 | 16 | Not Started | FALSE | Survey design pending
T092 | Refresh employer value proposition | HR | Alex Chen | 2026-09-12 | 2026-10-28 | 46 | In Progress | FALSE | Value proposition draft in review
T093 | Prepare product messaging guide | Marketing | Emily Davis | 2026-09-01 | 2026-09-25 | 24 | Completed | FALSE | Messaging guide approved
T094 | Coordinate seasonal campaign assets | Marketing | Sarah Johnson | 2026-09-20 | 2026-10-30 | 40 | In Progress | FALSE | Assets in production
T095 | Analyze paid campaign performance | Marketing | David Kim | 2026-08-15 | 2026-09-15 | 31 | Completed | FALSE | Campaign analysis delivered
T096 | Prepare customer webinar materials | Marketing | James Miller | 2026-10-02 | 2026-10-25 | 23 | Not Started | FALSE | Materials not yet prepared
T097 | Review content calendar | Marketing | Alex Chen | 2026-09-05 | 2026-10-12 | 37 | In Progress | FALSE | Calendar review in progress
T098 | Develop customer retention campaign | Marketing | Emily Davis | 2026-08-20 | 2026-09-25 | 36 | Completed | FALSE | Retention campaign plan approved
T099 | Prepare monthly KPI review | Finance | Sarah Johnson | 2026-10-04 | 2026-10-09 | 5 | Not Started | TRUE | KPI review scheduled
T100 | Consolidate year-end action items | Strategy | David Kim | 2026-10-07 | 2026-11-30 | 54 | In Progress | FALSE | Action items being consolidated
T101 | Conduct interview with new users | Strategy | Alex Chen | 2026-10-03 | 2026-10-15 | 12 | In Progress | FALSE | New features and painpoints
T102 | Upgrade Infrastructure | Strategy | Sarah Johnson | 2026-09-26 | 2026-10-30 | 34 | Completed | FALSE | External consultant engagement pending.
T103 | Evaluate Vendor Proposals for Logistics | Strategy | Emily Davis | 2026-09-27 | 2026-10-07 | 10 | In Progress | TRUE | Three proposals shortlisted for management review.
T104 | Draft Q1 Marketing Strategy | Strategy | Emily Davis | 2026-09-28 | 2026-10-18 | 20 | Completed | FALSE | Kick-off meeting scheduled next week.
T105 | Audit Internal Expense Reports | Finance | Emily Davis | 2026-09-29 | 2026-10-04 | 5 | Not Started | TRUE | Waiting for submission of all departmental reports.
Formulas:
Overdue? = AND(Table1[[#This Row],[Status]]<>"Completed",Table1[[#This Row],[Due Date]]<TODAY())
Task Management Tracker
Completed
In Progress
Not Started
Total
42
40
23
105
Overdue Tasks
13

## Support Sheet
Status | Count | Owners | Count | Team | Count | Overdue
Completed | 42 | Sarah Johnson | 25 | Finance | 27 | 13
In Progress | 40 | David Kim | 21 | Strategy | 32
Not Started | 23 | James Miller | 18 | HR | 25
Total | 105 | Alex Chen | 20 | Marketing | 21
|  | Emily Davis | 21